## CONSOLIDATED_PERFORMANCE
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Batangas State University TNEU ARASOF-Nasugbu
A. General Performance Indicator Status
Presents the consolidated performance indicators from the AOP, QEO, OPCR and OPMM, showing the target, accomplishment, variance, percentage of accomplishment, and status.
Indicator_ ID | Performance Indicator | Source | Target | Accomplishment | Variance | Status | Target per Person/Office Concerned
PI-01 | Number of faculty members who took the Basic and Advanced Course in Community Service | AOP, QEO, OPCR, OPMM | 10 | 10 | 0 | MET | CABEIHM - 2 CCJE - 2 CHS - 1 CICS - 1 CTE - 2 Laboratory School - 2
PI-02 | Number of approved extension programs conducted | QEO, OPMM | 13 | 1 | -12 | Partially MET | CABEIHM - 4 CAS - 4 CCJE - 1 CHS - 1 CICS - 1 CTE - 2
PI-03 | Number of external beneficiaries weighted by the length of training | QEO, OPMM | 1408 |  | -1408 | MET | CABEIHM - 436 CAS - 436 CCJE - 109 CHS - 109 CICS - 109 CTE - 218
PI-04 | Percentage of trainees who rate the training course at least satisfactory in terms of quality and relevance | QEO, OPMM | 97% | 100% | 3% | MET | CABEIHM - 97% CAS - 97% CCJE - 97% CHS - 97% CICS - 97% CTE - 97% Laboratory School - 97%
PI-05 | Number of notarized Memorandum of Understanding (MOU) / Memorandum of Agreement (MOA) | QEO, OPMM | 15 | 12 | -3 | Partially MET | CABEIHM - 3 CAS - 4 CCJE - 2 CHS - 2 CICS - 1 CTE - 2 Laboratory School - 1
PI-06 | Number of campus projects adopting COMLEX as a community development approach | AOP, OPMM | 1 | 1 | 0 | MET | CABEIHM - 1
PI-07 | Number of pool of experts organized per specialization | AOP, OPMM | 1 | 1 | 0 | MET | CAS - 1
PI-08 | Number of initial implementation of training for families and communities | AOP, OPMM | 1 | 1 | 0 | MET | CTE - 1
PI-09 | Number of social innovation projects utilized by the community | AOP, OPMM | 1 | 1 | 0 | MET | CICS - 1
PI-10 | Number of faculty members monitored who have completed and implemented the course | AOP, OPMM | 1 | 1 | 0 | MET | CABEIHM - 1 CICS - 1
PI-11 | Number of radio program episodes addressing emerging and pressing concerns aired/produced | AOP, OPMM | 1 | 1 | 0 | MET | CAS - 1
PI-12 | Number of livelihood and capacity-building trainings conducted | OPMM | 2 | 2 | 0 | MET | CABEIHM - 1 CAS - 1
PI-13 | Number of conducted technical advisory for industries and other institutions | OPMM | 11 | 11 | 0 | MET | CABEIHM - 3 CAS - 3 CCJE - 1 CHS - 1 CICS - 1 CTE - 2
PI-14 | Budget Utilization Rate | Budget | 70% | 0% | -70% | Partially MET | CABEIHM - 70% CAS - 70% CCJE - 70% CHS - 70% CICS - 70% CTE - 70% Laboratory School - 70%
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Informatics and Computing Sciences (CICS)
B. Extension Activities Implementation and Budget Utilization Status
Presents the implementation progress of approved extension activities, including planned and actual implementation dates, challenges and interventions, and the corresponding budget allocation and utilization.
No. | Activity Title | Target Implementation Date | Actual Implementation Date | Implementation Status | Budget Allocation | Budget Utilization | Budget Utilization Rate
PROGRAM USAD ¦ PROJECT 1 (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Strategic Partnership Coordination | Q4, 2025 | Q4, 2025 | Implemented | No University budget allocation was required since the activity was conducted online.
2 | MSME Profiling and Status Mapping in the MSMEs assisted under DTI-CARP | Q4, 2025 | Q4, 2025 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
3 | MOA Signing and Program Launching | Q4, 2025 | Q4, 2025 | Implemented | 12500 | 11000 | 88%
PROGRAM USAD ¦ PROJECT 2 (FISCAL YEAR 2025 IMPLEMENTATION)
4 | Photography for MSME Branding Workshop | Q4, 2025 | Q4, 2025 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
5 | Video Editing and Content Creation for Social Media | Q4, 2025 | Q4, 2025 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 3 (FISCAL YEAR 2026 IMPLEMENTATION)
6 | Digital Branding and Marketing Identity Masterclass | Q1, 2026 | Q1, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
7 | Website Development and Social Media Engagement Workshop | Q1, 2026 | Q1, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 4 (FISCAL YEAR 2026 IMPLEMENTATION)
8 | Community Data Center Launch, Orientation, and Onboarding | Q2, 2026 | Q2, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
9 | Data Privacy, Security, and Access Management Training | Q2, 2026 | Q2, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 5 (FISCAL YEAR 2026 IMPLEMENTATION)
10 | MSME Platform Technology Transfer and Training | Q3, 2026 | Q3, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
11 | Mobile App Dissemination and Awareness Campaign | Q3, 2026 | Q3, 2026 | For Implementation | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 6 (FISCAL YEAR 2026 IMPLEMENTATION)
12 | Data Analytics and KPI Measurement Workshop | Q4, 2026 | Q4, 2026 | For Implementation | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
13 | Sustainable IT Practices and Innovation Training | Q4, 2026 | Q4, 2026 | For Implementation | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Informatics and Computing Sciences (CICS)
C. Status of Report and Documentary Requirements Submission
Presents the compliance status of each extension activity with the required reports and supporting documents, including post-implementation and monitoring requirements.
No. | Activity Title | Attendance | Evaluation Report | Terminal Report | Monitoring Tool | Monitoring the Progress | Rescheduling Letters
PROGRAM USAD ¦ PROJECT 1
1 | Strategic Partnership Coordination | N/A | N/A | N/A | Submitted | Submitted | N/A
2 | MSME Profiling and Status Mapping in the MSMEs assisted under DTI-CARP | Submitted | N/A | N/A | Submitted | Submitted | N/A
3 | MOA Signing and Program Launching | Submitted | N/A | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 2
4 | Photography for MSME Branding Workshop | Submitted | Submitted | N/A | Submitted | Submitted | N/A
5 | Video Editing and Content Creation for Social Media | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 3
6 | Digital Branding and Marketing Identity Masterclass | Submitted | Submitted | N/A | Submitted | Submitted | N/A
7 | Website Development and Social Media Engagement Workshop | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 4
8 | Community Data Center Launch, Orientation, and Onboarding | Submitted | Submitted | N/A | Submitted | Submitted | N/A
9 | Data Privacy, Security, and Access Management Training | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 5
10 | MSME Platform Technology Transfer and Training | Submitted | Submitted | Not Yet Due | Not Yet Due | Not Yet Due | N/A
11 | Mobile App Dissemination and Awareness Campaign | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
PROGRAM USAD ¦ PROJECT 6
12 | Data Analytics and KPI Measurement Workshop | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
13 | Sustainable IT Practices and Innovation Training | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
Prepared by: |  |  | Reviewed and Verified: |  | Approved and Certified Correct:
Ms. MARICHELLE J. ABIOG |  |  | Dr. NOELYN M. DE JESUS |  | Dr. FROILAN G. DESTREZA
Staff, Extension Services Office |  |  | Head, Extension Services Office |  | Vice Chancellor for Research, Development, and Extension Services

## REF_CICS
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Informatics and Computing Sciences (CICS)
A. General Performance Indicator Status
Presents the consolidated performance indicators from the AOP, QEO, OPCR and OPMM, showing the target, accomplishment, variance, percentage of accomplishment, and status.
Indicator_ ID | Performance Indicator | Source | Target | Accomplishment | Variance | Status | Remarks
PI-01 | Number of faculty members who took the Basic and Advanced Course in Community Service | AOP, QEO, OPCR, OPMM | 1 | 1 | 0 | MET | Faculty Members who took the Advanced Course in Community Service: 1. Dr. Noelyn M. De Jesus
PI-02 | Number of approved extension programs conducted | QEO, OPMM | 1 | 0 | -1 | Partially MET | Two (2) activities remain for implementation in FY 2026: 1.Project 5 Activity 2 2. Project 6 Activity 1 3. Project 6 Activity 2
PI-03 | Number of external beneficiaries weighted by the length of training | QEO, OPMM | 109 | 101 | -8 | MET | Breakdown of beneficiaries weighted by length of training: 1. Project 3 Activity 1 - 25 2. Project 3 Activity 2 - 25 3. Project 4 Activity 1 - 17 4. Project 4 Activity 2 - 19 5. Project 5 Activity 1 - 15
PI-04 | Percentage of trainees who rate the training course at least satisfactory in terms of quality and relevance | QEO, OPMM | 97% | 100% | 3% | MET | Trainees rating the training satisfactory or higher per activity: 1. Project 3 Activity 1 - 100% 2. Project 3 Activity 2 - 100% 3. Project 4 Activity 1 - 100% 4. Project 4 Activity 2 - 100% 5. Project 5 Activity 1 - 100%
PI-05 | Number of notarized Memorandum of Understanding (MOU) / Memorandum of Agreement (MOA) | QEO, OPMM | 1 | 1 | 0 | MET | One (1) notarized MOA was established, meeting the annual target. 1. DTI Batangas
PI-09 | Number of social innovation projects utilized by the community | AOP, OPMM | 1 | 1 | 0 | MET | One (1) social innovation project was utilized by the partner community, meeting the annual target: 1. MSME Visibility Platform
PI-10 | Number of faculty members monitored who have completed and implemented the course | AOP, OPMM | 1 | 1 | 0 | MET | Faculty Member monitored who have completed and implemented the course: 1. Dr. Noelyn M. De Jesus
PI-13 | Number of conducted technical advisory for industries and other institutions | OPMM | 1 | 1 | 0 | MET | One (1) technical advisory service was conducted, meeting the annual target: 1. Project 4 Activity 2
PI-14 | Budget Utilization Rate | Budget | 70% | 88% | 18% | MET | Budget utilization remains above the established target.
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Informatics and Computing Sciences (CICS) - Unified, Smart, Accessible Data Center (USAD) Program
B. Extension Activities Implementation and Budget Utilization Status
Presents the implementation progress of approved extension activities, including planned and actual implementation dates, challenges and interventions, and the corresponding budget allocation and utilization.
Act. No. | Activity Title | Target Implementation Date | Actual Implementation Date | Implementation Status | Budget Allocation | Budget Utilization | Budget Utilization Rate
PROGRAM USAD ¦ PROJECT 1 LinkUp: Building Strategic Partnerships for MSME Digital Transformation (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Strategic Partnership Coordination | Q4, 2025 | Q4, 2025 | Implemented | No University budget allocation was required since the activity was conducted online.
2 | MSME Profiling and Status Mapping in the MSMEs assisted under DTI-CARP | Q4, 2025 | Q4, 2025 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
3 | MOA Signing and Program Launching | Q4, 2025 | Q4, 2025 | Implemented | 12500 | 11000 | 88%
PROGRAM USAD ¦ PROJECT 2 VisualEdge: Creative Photography and Video Editing for MSME Promotion (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Photography for MSME Branding Workshop | Q4, 2025 | Q4, 2025 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
2 | Video Editing and Content Creation for Social Media | Q4, 2025 | Q4, 2025 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 3 DigiMark: A Digital Marketing and Branding to Strengthen MSME Profit Growth (FISCAL YEAR 2026 IMPLEMENTATION)
1 | Digital Branding and Marketing Identity Masterclass | Q1, 2026 | Q1, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
2 | Website Development and Social Media Engagement Workshop | Q1, 2026 | Q1, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 4 DataNest: The Community’s Home for Smart and Sustainable Digital Access (FISCAL YEAR 2026 IMPLEMENTATION)
1 | Community Data Center Launch, Orientation, and Onboarding | Q2, 2026 | Q2, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
2 | Data Privacy, Security, and Access Management Training | Q2, 2026 | Q2, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 5 Glimpse: Technology Transfer and End-User Training for the MSME Visibility Platform (FISCAL YEAR 2026 IMPLEMENTATION)
1 | MSME Platform Technology Transfer and Training | Q3, 2026 | Q3, 2026 | Implemented | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
2 | Mobile App Dissemination and Awareness Campaign | Q3, 2026 | Q4, 2026 | For Implementation | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
PROGRAM USAD ¦ PROJECT 6 TechWise: Training on Sustainable IT Practices and KPI-Driven Innovation (FISCAL YEAR 2026 IMPLEMENTATION)
1 | Data Analytics and KPI Measurement Workshop | Q4, 2026 | Q4, 2026 | For Implementation | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
2 | Sustainable IT Practices and Innovation Training | Q4, 2026 | Q4, 2026 | For Implementation | No University budget was allocated, as food expenses for all participants, faculty, and student extensionists across all activities were fully shouldered by the partner agency.
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Informatics and Computing Sciences (CICS) - Unified, Smart, Accessible Data Center (USAD) Program
C. Status of Report and Documentary Requirements Submission
Presents the compliance status of each extension activity with the required reports and supporting documents, including post-implementation and monitoring requirements.
No. | Activity Title | Attendance | Evaluation Report | Terminal Report | Monitoring Tool | Monitoring the Progress | Rescheduling Letters
PROGRAM USAD ¦ PROJECT 1 LinkUp: Building Strategic Partnerships for MSME Digital Transformation (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Strategic Partnership Coordination | N/A | N/A | N/A | Submitted | Submitted | N/A
2 | MSME Profiling and Status Mapping in the MSMEs assisted under DTI-CARP | Submitted | N/A | N/A | Submitted | Submitted | N/A
3 | MOA Signing and Program Launching | Submitted | N/A | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 2 VisualEdge: Creative Photography and Video Editing for MSME Promotion (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Photography for MSME Branding Workshop | Submitted | Submitted | N/A | Submitted | Submitted | N/A
2 | Video Editing and Content Creation for Social Media | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 3 DigiMark: A Digital Marketing and Branding to Strengthen MSME Profit Growth (FISCAL YEAR 2026 IMPLEMENTATION)
1 | Digital Branding and Marketing Identity Masterclass | Submitted | Submitted | N/A | Submitted | Submitted | N/A
2 | Website Development and Social Media Engagement Workshop | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 4 DataNest: The Community’s Home for Smart and Sustainable Digital Access (FISCAL YEAR 2026 IMPLEMENTATION)
1 | Community Data Center Launch, Orientation, and Onboarding | Submitted | Submitted | N/A | Submitted | Submitted | N/A
2 | Data Privacy, Security, and Access Management Training | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM USAD ¦ PROJECT 5 Glimpse: Technology Transfer and End-User Training for the MSME Visibility Platform (FISCAL YEAR 2026 IMPLEMENTATION)
1 | MSME Platform Technology Transfer and Training | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
2 | Mobile App Dissemination and Awareness Campaign | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
PROGRAM USAD ¦ PROJECT 6 TechWise: Training on Sustainable IT Practices and KPI-Driven Innovation (FISCAL YEAR 2026 IMPLEMENTATION)
1 | Data Analytics and KPI Measurement Workshop | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
2 | Sustainable IT Practices and Innovation Training | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
Prepared by: |  |  | Reviewed and Verified: |  | Approved and Certified Correct:
Ms. MARICHELLE J. ABIOG |  |  | Dr. NOELYN M. DE JESUS |  | Dr. FROILAN G. DESTREZA
Staff, Extension Services Office |  |  | Head, Extension Services Office |  | Vice Chancellor for Research, Development, and Extension Services

## REF_CHS
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Health and Sciences (CHS)
A. General Performance Indicator Status
Presents the consolidated performance indicators from the AOP, QEO, OPCR and OPMM, showing the target, accomplishment, variance, percentage of accomplishment, and status.
No. | Performance Indicator | Source | Target | Accomplishment | Variance | Status | Remarks
1 | Number of faculty members who took the Basic and Advanced Course in Community Service | AOP, QEO, OPCR, OPMM | 1 | 1 | 0 | MET | Faculty Members who took the Advanced Course in Community Service: 1. Ms. Kareen C. Aclan
2 | Number of approved extension programs conducted | QEO, OPMM | 1 | 1 | 0 | MET | All planned activities under the approved extension program were successfully implemented.
3 | Number of external beneficiaries weighted by the length of training | QEO, OPMM | 109 | 475 | 366 | MET | Breakdown of beneficiaries weighted by length of training: 1. Project 1 Activity 2 Q1 - 54 2. Project 1 Activity 3 Q1 - 54 3. Project 1 Activity 4 Q1 - 57 4. Project 2 Activity 1 - 38 5. Project 2 Activity 2 - 38 6. Project 2 Activity 3 - 36 7. Project 1 Activity 2 Q3 - 69 8. Project 1 Activity 3 Q3 - 66 9. Project 1 Activity 4 Q3 - 63
4 | Percentage of trainees who rate the training course at least satisfactory in terms of quality and relevance | QEO, OPMM | 97% | 100% | 3% | MET | Trainees rating the training satisfactory or higher per activity: 1. Project 1 Activity 2 Q1 - 100% 2. Project 1 Activity 3 Q1 - 100% 3. Project 1 Activity 4 Q1 - 100% 4. Project 2 Activity 1 - 100% 5. Project 2 Activity 2 - 100% 6. Project 2 Activity 3 - 100% 7. Project 1 Activity 2 Q3 - 100% 8. Project 1 Activity 3 Q3 - 100% 9. Project 1 Activity 4 Q3 - 100%
5 | Number of notarized Memorandum of Understanding (MOU) / Memorandum of Agreement (MOA) | QEO, OPMM | 2 | 1 | -1 | Partially MET | One (1) notarized MOA was established, with one (1) additional MOA in process: 1. MHO Lian (established) 2. MHO Nasugbu (for signing)
6 | Number of conducted technical advisory for industries and other institutions | OPMM | 1 | 1 | 0 | MET | One (1) technical advisory service was conducted, meeting the annual target: 1. Project 1 Activity 3
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Health and Sciences (CHS) - Collaborative Health Solutions 1.0: Capability-building, Advocacy, Response, Education, and Support for Health and Sustainability (CHS CARES)
B. Extension Activities Implementation and Budget Utilization Status
Presents the implementation progress of approved extension activities, including planned and actual implementation dates, challenges and interventions, and the corresponding budget allocation and utilization.
No. | Activity Title | Target Implementation Date | Actual Implementation Date | Implementation Status | Budget Allocation | Budget Utilization | Budget Utilization Rate
PROGRAM CHS CARES ¦ PROJECT 1 KaKaTuWaNu: Kaalaman, Kahandaan Tungo sa Wastong Nutrisyon (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Memorandum of Agreement (MOA) Preparation and Signing with Nasugbu and Lian | Q3, 2025 | Q3, 2025 | Implemented | No budget allocation was required, as no formal MOA/MOU signing ceremony was planned.
2 | Bridging the Digital Gap for Barangay Nutritional Scholars with Basic Computer Training for E-OPT Success | Q3, 2025 | Q3, 2025 | Implemented | 11600 | 10800 | 93.1%
3 | E-OPT Plus Tool Version 2.0 Training for Barangay Nutrition Scholars | Q3, 2025 | Q3, 2025 | Implemented | 10800 | 10800 | 100%
4 | ABCD Nutritional Assessment for Barangay Nutrition Scholars | Q3, 2025 | Q3, 2025 | Implemented | 11600 | 10800 | 93.1%
PROGRAM CHS CARES ¦ PROJECT 2 KaKaTuWaKa: Kaalaman, Kahandaan Tungo sa Wastong Kalusugan (FISCAL YEAR 2025 IMPLEMENTATION)
1 | First Aid, Vital Signs, and Communication for BHWs | Q3, 2025 | Q3, 2025 | Implemented | 7250 | 6000 | 82.76%
2 | DOH Programs for BHWs | Q3, 2025 | Q3, 2025 | Implemented | 6750 | 6000 | 88.89%
3 | Communicable and Non-communicable Diseases | Q3, 2025 | Q3, 2025 | Implemented | 7250 | 6000 | 82.76%
PROGRAM CHS CARES ¦ PROJECT 1 KaKaTuWaNu: Kaalaman, Kahandaan Tungo sa Wastong Nutrisyon (FISCAL YEAR 2026 QUARTER 1 IMPLEMENTATION)
2 | Bridging the Digital Gap for Barangay Nutritional Scholars with Basic Computer Training for E-OPT Success | Q1, 2026 | Q1, 2026 | Implemented | 11600 | 10400 | 89.66%
3 | E-OPT Plus Tool Version 2.0 Training for Barangay Nutrition Scholars | Q1, 2026 | Q1, 2026 | Implemented | 10800 | 9600 | 88.89%
4 | ABCD Nutritional Assessment for Barangay Nutrition Scholars | Q1, 2026 | Q1, 2026 | Implemented | 11600 | 10400 | 89.66%
PROGRAM CHS CARES ¦ PROJECT 2 KaKaTuWaKa: Kaalaman, Kahandaan Tungo sa Wastong Kalusugan (FISCAL YEAR 2026 IMPLEMENTATION)
1 | First Aid, Vital Signs, and Communication for BHWs | Q2, 2026 | Q2, 2026 | Implemented | 7250 | 6750 | 93.1%
2 | DOH Programs for BHWs | Q2, 2026 | Q2, 2026 | Implemented | 6750 | 6250 | 92.59%
3 | Communicable and Non-communicable Diseases | Q2, 2026 | Q2, 2026 | Implemented | 7250 | 6750 | 93.1%
PROGRAM CHS CARES ¦ PROJECT 1 KaKaTuWaNu: Kaalaman, Kahandaan Tungo sa Wastong Nutrisyon (FISCAL YEAR 2026 QUARTER 3 IMPLEMENTATION)
2 | Bridging the Digital Gap for Barangay Nutritional Scholars with Basic Computer Training for E-OPT Success | Q3, 2026 | Q3, 2026 | Implemented | 12180 | For Disbursement | -
3 | E-OPT Plus Tool Version 2.0 Training for Barangay Nutrition Scholars | Q3, 2026 | Q3, 2026 | Implemented | 11340 | For Disbursement | -
4 | ABCD Nutritional Assessment for Barangay Nutrition Scholars | Q3, 2026 | Q3, 2026 | Implemented | 12180 | For Disbursement | -
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Health and Sciences (CHS) - Collaborative Health Solutions 1.0: Capability-building, Advocacy, Response, Education, and Support for Health and Sustainability (CHS CARES)
C. Status of Report and Documentary Requirements Submission
Presents the compliance status of each extension activity with the required reports and supporting documents, including post-implementation and monitoring requirements.
No. | Activity Title | Attendance | Evaluation Report | Terminal Report | Monitoring Tool | Monitoring the Progress | Rescheduling Letters
PROGRAM CHS CARES ¦ PROJECT 1 KaKaTuWaNu: Kaalaman, Kahandaan Tungo sa Wastong Nutrisyon (FISCAL YEAR 2025 IMPLEMENTATION)
1 | Memorandum of Agreement (MOA) Preparation and Signing with Nasugbu and Lian | N/A | N/A | N/A | Submitted | Submitted | N/A
2 | Bridging the Digital Gap for Barangay Nutritional Scholars with Basic Computer Training for E-OPT Success | Submitted | Submitted | N/A | Submitted | Submitted | N/A
3 | E-OPT Plus Tool Version 2.0 Training for Barangay Nutrition Scholars | Submitted | Submitted | N/A | Submitted | Submitted | N/A
4 | ABCD Nutritional Assessment for Barangay Nutrition Scholars | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM CHS CARES ¦ PROJECT 2 KaKaTuWaKa: Kaalaman, Kahandaan Tungo sa Wastong Kalusugan (FISCAL YEAR 2025 IMPLEMENTATION)
5 | First Aid, Vital Signs, and Communication for BHWs | Submitted | Submitted | N/A | Submitted | Submitted | N/A
6 | DOH Programs for BHWs | Submitted | Submitted | N/A | Submitted | Submitted | N/A
7 | Communicable and Non-communicable Diseases | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM CHS CARES ¦ PROJECT 1 KaKaTuWaNu: Kaalaman, Kahandaan Tungo sa Wastong Nutrisyon (FISCAL YEAR 2026 QUARTER 1 IMPLEMENTATION)
8 | Bridging the Digital Gap for Barangay Nutritional Scholars with Basic Computer Training for E-OPT Success | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
9 | E-OPT Plus Tool Version 2.0 Training for Barangay Nutrition Scholars | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
10 | ABCD Nutritional Assessment for Barangay Nutrition Scholars | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM CHS CARES ¦ PROJECT 2 KaKaTuWaKa: Kaalaman, Kahandaan Tungo sa Wastong Kalusugan (FISCAL YEAR 2026 IMPLEMENTATION)
11 | First Aid, Vital Signs, and Communication for BHWs | Submitted | Submitted | N/A | Submitted | Submitted | N/A
12 | DOH Programs for BHWs | Submitted | Submitted | N/A | Submitted | Submitted | N/A
13 | Communicable and Non-communicable Diseases | Submitted | Submitted | N/A | Submitted | Submitted | N/A
PROGRAM CHS CARES ¦ PROJECT 1 KaKaTuWaNu: Kaalaman, Kahandaan Tungo sa Wastong Nutrisyon (FISCAL YEAR 2026 QUARTER 3 IMPLEMENTATION)
14 | Bridging the Digital Gap for Barangay Nutritional Scholars with Basic Computer Training for E-OPT Success | Pending | Pending | Pending | Pending | Pending | N/A
15 | E-OPT Plus Tool Version 2.0 Training for Barangay Nutrition Scholars | Pending | Pending | Pending | Pending | Pending | N/A
16 | ABCD Nutritional Assessment for Barangay Nutrition Scholars | Pending | Pending | Pending | Pending | Pending | N/A
Prepared by: |  |  | Reviewed and Verified: |  | Approved and Certified Correct:
Ms. MARICHELLE J. ABIOG |  |  | Dr. NOELYN M. DE JESUS |  | Dr. FROILAN G. DESTREZA
Staff, Extension Services Office |  |  | Head, Extension Services Office |  | Vice Chancellor for Research, Development, and Extension Services

## REF_CTE
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Teacher Education (CTE)
A. General Performance Indicator Status
Presents the consolidated performance indicators from the AOP, QEO, OPCR and OPMM, showing the target, accomplishment, variance, percentage of accomplishment, and status.
No. | Performance Indicator | Source | Target | Accomplishment | Variance | Status | Remarks
1 | Number of faculty members who took the Basic and Advanced Course in Community Service | AOP, QEO, OPCR, OPMM | 1 | 1 | 0 | MET | Faculty Members who took the Advanced Course in Community Service: 1. Mr. John Cloyd Pajo
2 | Number of approved extension programs conducted | QEO, OPMM | 2 | 0 | -2 | Partially MET | Two (2) approved extension programs, TELA and TEACHER, have remaining activities scheduled for implementation within Q3-Q4 2026. Program TELA: Fifteen (15) extension activities are scheduled for implementation, covering, 1. Project 3 Activity 2-5 (Batch 1) 2. Project 2 Activity 1-4 (Batch 2) 3. Project 3 Activity 2-5 (Batch 2) 4. Project 4 Activity 1-3 (All) Program TEACHER: Nine (9) extension activities are scheduled for implementation, covering, 1. Project 1 Activity 8-10 2. Project 2 Activity 8-10 3. Project 3 Activity 8-10
3 | Number of external beneficiaries weighted by the length of training | QEO, OPMM | 109 |  | -109 | Partially MET | 101 of the 109 target beneficiaries have been served. The remaining target is expected to be achieved through the three (3) extension activities scheduled in Q4 2026.
4 | Percentage of trainees who rate the training course at least satisfactory in terms of quality and relevance | QEO, OPMM | 97% | 100% | 3% | Partially MET | Target exceeded by 3 percentage points, with all evaluated trainees rating the training as satisfactory in terms of quality and relevance.
5 | Number of notarized Memorandum of Understanding (MOU) / Memorandum of Agreement (MOA) | QEO, OPMM | 4 | 1 | -3 | Partially MET | One (1) notarized MOA was established, meeting the annual target, 2 are still pending 1. Calatagan SDO Office - Established 2. Brgy. Wawa, Nasugbu - Pending 3. DSWD - Pending 4. Maugat Council - Pending
6 | Number of initial implementation of training for families and communities | AOP, OPMM | 1 | 1 | 0 | MET | Development of the training module for families and communities is completed and submitted in the Extension Services Office.
7 | Number of conducted technical advisory for industries and other institutions | OPMM | 1 | 1 | 0 | MET | One (1) technical advisory service was conducted, meeting the annual target: 1. Project 3 Activity 7
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Teacher Education (CTE) - PROGRAM TEACHER (Teaching Excellence and Competency in Holistic Education Research)
B. Extension Activities Implementation and Budget Utilization Status
Presents the implementation progress of approved extension activities, including planned and actual implementation dates, challenges and interventions, and the corresponding budget allocation and utilization.
No. | Activity Title | Target Implementation Date | Actual Implementation Date | Implementation Status | Budget Allocation | Budget Utilization | Budget Utilization Rate
PROGRAM TELA - Project 3 Basics of Burda (Batch 1)
1 | Benchmarking Activity for Embroidery | Q4, 2025 | Q4, 2026 | Rescheduled | - | - | -
2 | Seminar and Workshop on the Basics of Embroidery | Q4, 2025 | Q4, 2026 | Rescheduled | 49100 | 0 | 0%
3 | Hands-on Embroidery | Q4, 2025 | Q4, 2026 | Rescheduled
4 | Basics of Barong and Filipiniana | Q4, 2025 | Q4, 2026 | Rescheduled
5 | Sewing and Assembling Barong and Filipiniana | Q4, 2025 | Q4, 2026 | Rescheduled
PROGRAM TELA - Project 2 Basics of School Apparel making (Batch 2)
6 | Pattern Making | Q2, 2026 | Q4, 2026 | Rescheduled | 152775 | 0 | 0%
7 | Sewing Upper Garments | Q2, 2026 | Q4, 2026 | Rescheduled
8 | Tailoring Lower Garments | Q2, 2026 | Q4, 2026 | Rescheduled
9 | Learning Robes and Gowns | Q2, 2026 | Q4, 2026 | Rescheduled
PROGRAM TELA - Project 3 Basics of Burda (Batch 2)
10 | Seminar and Workshop on the Basics of Embroidery | Q2, 2026 | Q4, 2026 | Rescheduled | 90405 | 0 | 0%
11 | Hands-on Embroidery | Q2, 2026 | Q4, 2026 | Rescheduled
12 | Basics of Barong and Filipiniana | Q2, 2026 | Q4, 2026 | Rescheduled
13 | Sewing and Assembling Barong and Filipiniana | Q2, 2026 | Q4, 2026 | Rescheduled
PROGRAM TELA - Project 4 Basics for Business Expansion and Personal Development
14 | Seminar and Workshop Financial Literacy | Q3, 2026 | Q4, 2026 | Rescheduled | 10400 | 0 | 0%
15 | Seminar and Workshop on Digitalization of Products | Q3, 2026 | Q4, 2026 | Rescheduled | 10400 | 0 | 0%
16 | Seminar and Workshop on Organization Formation | Q3, 2026 | Q4, 2026 | Rescheduled | 10400 | 0 | 0%
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
College: College of Teacher Education (CTE) - PROGRAM TEACHER (Teaching Excellence and Competency in Holistic Education Research)
B. Extension Activities Implementation and Budget Utilization Status
Presents the implementation progress of approved extension activities, including planned and actual implementation dates, challenges and interventions, and the corresponding budget allocation and utilization.
No. | Activity Title | Target Implementation Date | Actual Implementation Date | Implementation Status | Budget Allocation | Budget Utilization | Budget Utilization Rate
PROGRAM TEACHER - PPROJECT 1
1 | Research Problems and Formulation | Q1, 2026 | Q1, 2026 | Implemented | 2500 | 2000 | 80%
2 | Data Analysis and Interpretation in Research | Q2, 2026 | Q1, 2026 | Implemented | 2500 | 2250 | 90%
3 | Onwards to the Basics of Presentation and Publication | Q2, 2026 | Q1, 2026 | Implemented | 2500 | 1500 | 60%
4 | Bridging Teaching and Research | Q3, 2026 | Q3, 2026 | Implemented | 2500 | Allocated food budget was not utilized, as the activity was conducted online.
5 | Research Ideation and Writing | Q3, 2026 | Q4, 2026 | For Implementation | 2500 | 0 | 0%
6 | Teaching and Learning Research Colloquium | Q4, 2026 | Q4, 2026 | For Implementation | 2500 | 0 | 0%
PROGRAM TEACHER - PPROJECT 2
7 | Research Problems and Formulation | Q1, 2026 | Q1, 2026 | Implemented | 2500 | 2000 | 80%
8 | Data Analysis and Interpretation in Research | Q2, 2026 | Q1, 2026 | Implemented | 2500 | 2250 | 90%
9 | Onwards to the Basics of Presentation and Publication | Q2, 2026 | Q1, 2026 | Implemented | 2500 | 1500 | 60%
10 | Bridging Teaching and Research | Q3, 2026 | Q3, 2026 | Implemented | 2500 | Allocated food budget was not utilized, as the activity was conducted online.
11 | Research Ideation and Writing | Q3, 2026 | Q4, 2026 | For Implementation | 2500 | 0 | 0%
12 | Teaching and Learning Research Colloquium | Q4, 2026 | Q4, 2026 | For Implementation | 2500 | 0 | 0%
PROGRAM TEACHER - PPROJECT 3
13 | Research Problems and Formulation | Q1, 2026 | Q1, 2026 | Implemented | 2500 | 2000 | 80%
14 | Data Analysis and Interpretation in Research | Q2, 2026 | Q1, 2026 | Implemented | 2500 | 2250 | 90%
15 | Onwards to the Basics of Presentation and Publication | Q2, 2026 | Q1, 2026 | Implemented | 2500 | 1500 | 60%
16 | Bridging Teaching and Research | Q3, 2026 | Q3, 2026 | Implemented | 2500 | Allocated food budget was not utilized, as the activity was conducted online.
17 | Research Ideation and Writing | Q3, 2026 | Q4, 2026 | For Implementation | 2500 | 0 | 0%
18 | Teaching and Learning Research Colloquium | Q4, 2026 | Q4, 2026 | For Implementation | 2500 | 0 | 0%
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - FY 2026
College: College of Teacher Education (CTE) - PROGRAM TELA (Tailoring Expertise and Learning in Apparel production): Livelihood and Entrepreneurial Empowerment for fisherfolk's families in Brgy. Wawa. Nasugbu, Batangas
C. Status of Report and Documentary Requirements Submission
Presents the compliance status of each extension activity with the required reports and supporting documents, including post-implementation and monitoring requirements.
No. | Activity Title | Attendance | Evaluation Report | Terminal Report | Monitoring Tool | Monitoring the Progress | Rescheduling Letters
PROGRAM TELA - Project 3 Basics of Burda (Batch 1)
1 | Benchmarking Activity for Embroidery | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Submitted
2 | Seminar and Workshop on the Basics of Embroidery | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Submitted
3 | Hands-on Embroidery | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Submitted
4 | Basics of Barong and Filipiniana | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Submitted
5 | Sewing and Assembling Barong and Filipiniana | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Submitted
PROGRAM TELA - Project 2 Basics of School Apparel making (Batch 2)
6 | Pattern Making | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
7 | Sewing Upper Garments | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
8 | Tailoring Lower Garments | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
9 | Learning Robes and Gowns | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
PROGRAM TELA - Project 3 Basics of Burda (Batch 2)
10 | Seminar and Workshop on the Basics of Embroidery | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
11 | Hands-on Embroidery | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
12 | Basics of Barong and Filipiniana | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
13 | Sewing and Assembling Barong and Filipiniana | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
PROGRAM TELA - Project 4 Basics for Business Expansion and Personal Development
14 | Seminar and Workshop Financial Literacy | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
15 | Seminar and Workshop on Digitalization of Products | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
16 | Seminar and Workshop on Organization Formation | Overdue | Overdue | Not Yet Due | Not Yet Due | Not Yet Due | Pending
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - FY 2026
College: College of Teacher Education (CTE) - PROGRAM TELA (Tailoring Expertise and Learning in Apparel production): Livelihood and Entrepreneurial Empowerment for fisherfolk's families in Brgy. Wawa. Nasugbu, Batangas
C. Status of Report and Documentary Requirements Submission
Presents the compliance status of each extension activity with the required reports and supporting documents, including post-implementation and monitoring requirements.
No. | Activity Title | Attendance | Evaluation Report | Terminal Report | Monitoring Tool | Monitoring the Progress | Rescheduling Letters
PROGRAM TEACHER - PPROJECT 1
1 | Research Problems and Formulation | Submitted | Submitted | N/A | Submitted | Submitted | N/A
2 | Data Analysis and Interpretation in Research | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
3 | Onwards to the Basics of Presentation and Publication | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
4 | Bridging Teaching and Research | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
5 | Research Ideation and Writing | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
6 | Teaching and Learning Research Colloquium | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
PROGRAM TEACHER - PPROJECT 2
7 | Research Problems and Formulation | Submitted | Submitted | N/A | Submitted | Submitted | N/A
8 | Data Analysis and Interpretation in Research | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
9 | Onwards to the Basics of Presentation and Publication | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
10 | Bridging Teaching and Research | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
11 | Research Ideation and Writing | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
12 | Teaching and Learning Research Colloquium | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
PROGRAM TEACHER - PPROJECT 2
13 | Research Problems and Formulation | Submitted | Submitted | N/A | Submitted | Submitted | N/A
14 | Data Analysis and Interpretation in Research | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
15 | Onwards to the Basics of Presentation and Publication | Submitted | Submitted | N/A | Submitted | Submitted | Submitted
16 | Bridging Teaching and Research | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
17 | Research Ideation and Writing | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
18 | Teaching and Learning Research Colloquium | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | N/A
Prepared by: |  |  | Reviewed and Verified: |  | Approved and Certified Correct:
Ms. MARICHELLE J. ABIOG |  |  | Dr. NOELYN M. DE JESUS |  | Dr. FROILAN G. DESTREZA
Staff, Extension Services Office |  |  | Head, Extension Services Office |  | Vice Chancellor for Research, Development, and Extension Services

## REF_LAB_SCHOOL
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
Department: Laboratory School
A. General Performance Indicator Status
Presents the consolidated performance indicators from the AOP, QEO, OPCR and OPMM, showing the target, accomplishment, variance, percentage of accomplishment, and status.
No. | Performance Indicator | Source | Target | Accomplishment | Variance | Status | Remarks
1 | Number of faculty members who took the Basic and Advanced Course in Community Service | AOP, QEO, OPCR, OPMM | 1 | 1 | 0 | MET | Faculty Members who took the Advanced Course in Community Service: 1. Asst. Prof. Ma. Fe M. Bagon
2 | Number of approved extension programs conducted | QEO, OPMM | 1 | 0 | -1 | Not Yet Due | Two (2) activities under the approved extension program are scheduled for implementation on September 25, 2026, following the status reporting date: 1. Project 1 Activity 3 2. Project 1 Activity 4
3 | Number of external beneficiaries weighted by the length of training | QEO, OPMM | 109 | 0 | -109 | Not Yet Due | Target beneficiaries are expected to be served during the extension activity scheduled on September 25, 2026.
4 | Percentage of trainees who rate the training course at least satisfactory in terms of quality and relevance | QEO, OPMM | 97% | 0% | -97% | Not Yet Due | Trainee satisfaction will be evaluated upon completion of the extension activity scheduled on September 25, 2026.
5 | Number of notarized Memorandum of Understanding (MOU) / Memorandum of Agreement (MOA) | QEO, OPMM | 1 | 1 | 0 | MET | One (1) notarized MOA was established, meeting the annual target. 1. Marian Learning Center
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
Department: Laboratory School
B. Extension Activities Implementation and Budget Utilization Status
Presents the implementation progress of approved extension activities, including planned and actual implementation dates, challenges and interventions, and the corresponding budget allocation and utilization.
No. | Activity Title | Target Implementation Date | Actual Implementation Date | Implementation Status | Budget Allocation | Budget Utilization | Budget Utilization Rate
1 | Training/Seminar in Basic Lego Robotics Programming | Q1, 2026 | Q3, 2026 | Implemented | 4500 | 0 | 0%
2 | Training/Seminar in Advanced Lego Robotics Programming | Q3, 2026 | Q3, 2026 | Implemented | 4500 | 0 | 0%
CONSOLIDATED EXTENSION PERFORMANCE AND BUDGET STATUS REPORT
Extension Services - Quarter 3 FY 2026
Department: Laboratory School
C. Status of Report and Documentary Requirements Submission
Presents the compliance status of each extension activity with the required reports and supporting documents, including post-implementation and monitoring requirements.
No. | Activity Title | Attendance | Evaluation Report | Terminal Report | Monitoring Tool | Monitoring the Progress | Rescheduling Letters
1 | Training/Seminar in Basic Lego Robotics Programming | Overdue | Overdue | Pending | Overdue | Overdue | Submitted
2 | Training/Seminar in Advanced Lego Robotics Programming | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Not Yet Due | Submitted
Prepared by: |  |  | Reviewed and Verified: |  | Approved and Certified Correct:
Ms. MARICHELLE J. ABIOG |  |  | Dr. NOELYN M. DE JESUS |  | Dr. FROILAN G. DESTREZA
Staff, Extension Services Office |  |  | Head, Extension Services Office |  | Vice Chancellor for Research, Development, and Extension Services